## Ref (hidden)
Category | Priority | Affiliate | Consume Type
Bugs | Low | ALL | Maintenance
Improvement | Medium | PASI | PO
Change Request | High | PEMI
Q&A |  | JAI
Others |  | SAI
SAMI
SAMI-JF

## Issue List (Jan 2023)
ISSUE LIST |  |  |  | Status/ Category | Open | UAT | Closed | TBC | Total | Man-Days | [7 empty] | Summary (Dec 2021) | Month | Man-Days
COMPANY |  | PT. Autocomp System Indonesia (PASI) |  | Bugs | 0 | 0 | 1 | 1 | 2 | 0 | [7 empty] | Previous Balance | 2022-12-31 | 52.5
PROJECT NAME |  | PASI Maintenance Project |  | CR | 3 | 2 | 0 | 0 | 5 | 0 | [7 empty] | Consumption from Issue List | 2023-01-01 | 1
PERIOD |  | July 2021 - June 2022 |  | Q&A | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Consumption from Visit | 2023-01-01 | 0
MAN-DAYS QUOTA |  | 100 Days |  | Support | 0 | 0 | 2 | 0 | 2 | 1 | [7 empty] | Ending Balance | 2023-01-01 | 51.5
REVISED DATE |  | 2022-03-01 |  | PO | 0 | 0 | 0 | 0 | 0 | 0
REVISED BY |  | TOS - Bayu, Yudha |  | Total (Exclude PO) | 3 | 2 | 3 | 1 | 9 | 1
Mandays Consumption
NO. | DATE | DESCRIPTION | SYSTEM | MODUL | CATEGORY | PRIORITY | PIC (PASI) | PIC (TOS) | AFFILIATE | STATUS | DUE DATE | DELIVERY DATE | CLOSED DATE | COMMENTS (HISTORICAL) | Consumption Type | REF NO./ PO NO. | REF DATE/ PO DATE | DESCRIPTION | MAN-DAYS | [7 empty] | Remark
| DATE | DESCRIPTION | SYSTEM | MODUL | CATEGORY | PRIORITY | ASSIGNEE | RAISED BY | AFFILIATE | DUE DATE | DUE DATE |  |  | COMMENTS |  |  |  |  | URS | DESIGN | DEV | TEST | IMPL | CHECK | DATA | TOTAL
2018-11-001 | 2018-11-01 | 1 Nov-12 Dec (Selalu ada Kanban Pending Terkirim), karena size file besar. Sehingga process send tidak terkirim. | PPS Batch Process - Send To Supplier | Send DN Template to Supplier | CR | Medium | Andik, Ulul | Fikri | PASI | Open | 2022-07-29 |  |  | - Request Man day to vendor and Inform to member PJ - Add screen monitoring timeout - Buat program untuk download data DN supplier. - Cek Logic Upload (keluar dialog box) 9 Dec 2019 (Fixed) 1. Deliver Program : 11 May 2020 2. Deliver Test Evidence : 23 May 2020 3. Test with Pak Andik : 15 Jun 2020 (NG, program exit when Process) Status : Re-schedule Due Date | Maintenance | 2018-11-001 | 2018-11-01 | Create new function to Upload/Download excel template manually | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Use 2018-2019 Mandays
2018-12-001 | 2018-12-15 | Forecast monthly report tidak sesuai dengan request, compare fluktuasi belum tersedia | PPS Web - Domestic | Historical Monthly Forecast | CR | Medium | Andik, Ulul, Bowo | Rizal | PASI | Open | 2020-05-08 | 2020-05-08 |  | 1. Deliver Program : 8 May 2020 (Test Environtment) 2. Update to Live Environtment : 11 May 2020 3. Deliver Test Evidence : 23 May 2020 Status : Re-schedule Due Date | Maintenance | 2018-12-001 | 2018-12-15 | Create new report Historical Monthly Forecast | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Use 2018-2019 Mandays
2021-05-001 | 2021-05-19 | Data master table ms_item di kolom assy code duplicate dari hasil interface Oracle ke DRMS. Procedure DRMS interface "sp_GetASSYLISTFromOracle" | DRMS | Interface Oracle - DRMS (ms_item) | Bugs | Medium | Andik | Bayu | PASI | TBC |  |  |  |  | Maintenance | 2021-05-001 | 2021-05-19 | Data master table ms_item di kolom assy code duplicate dari hasil interface Oracle ke DRMS. Procedure DRMS interface "sp_GetASSYLISTFromOracle" | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2021-10-002 | 2021-10-12 | Modify Input Indirect Activity add NIK | In Out Attendance | Input Indirect Activity | CR | High | Andik | Bayu | PASI | UAT | 2022-05-20 | 2022-05-19 |  | Ref No. CR PASI DRMS-21-22-001 Approved date: 23 Mar 2022 | Maintenance | 2021-10-002 | 2021-10-12 | Modify Input Indirect Activity add NIK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-09-001 | 2022-09-02 | Input Down Time for Pre Assy & Final Assy - Assy No. input for final assy is mandatory - Select all as default for input man power in grid | DRMS | Input Down Time | CR | High | Andik | Bayu | PASI | UAT | 2022-10-26 | 2022-10-20 |  | Ref No. CR PASI DRMS-22-23-001 Send document: 20 Sep 2022 Approve date: 11 Oct 2022 | Maintenance | 2022-09-001 | 2022-09-02 | Input Down Time for Pre Assy & Final Assy - Assy No. input for final assy is mandatory - Select all as default for input man power in grid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-10-004 | 2022-10-07 | EDI PO Export | EDI OES PO | EDI OES PO | Bugs | High | Andik | Yuda | PASI | Closed | 2022-11-04 | 2022-11-10 | 2023-01-19 | 10 Nov 2022 : File sampel sudah bisa dibaca, tetapi kena validasi Time Chart. Data masuk setelah validasi dilepas. 19 Jan 2022 : Penambahan beberapa validasi disesuaikan dengan flow process | Maintenance | 2022-10-003 | 2022-10-07 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-12-001 | 2022-12-21 | New function to split delivery data by select box number | PPS Web - Export | DELIVERY, RECEIVING AND SHIPPING (EXPORT) | CR | High | Andik | Yuda | PASI | Open | 2023-03-18 |  |  | Design confirmation at 16 Jan 2023 Reschedule Due Date | Maintenance | 2022-12-001 | 2022-12-21 | New function to split delivery data by select box number | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mandays consump at Dec 2022
2023-01-001 | 2023-01-09 | Prefix Kanban Barcode | PPS Web - Domestic | Kanban Barcode | Support | High | Galih | Fikri | PASI | Closed | 2023-01-09 | 2023-01-09 | 2023-01-09 | Prefix Kanban bisa 2 characters | Maintenance | 2023-01-001 | 2023-01-09 | Prefix Kanban bisa 2 characters | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5
2023-01-002 | 2023-01-19 | Perbedaan Price di Receiving | PPS Web - Export | Summary Progresss Export | Support | High | Galih | Fikri | PASI | Closed | 2023-01-19 | 2023-01-19 | 2023-01-19 | Perbedaan Price di Transaksi dengan Master | Maintenance | 2023-01-002 | 2023-01-19 | Perbedaan Price di Transaksi dengan Master | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Month = [Month, row below]-1
Month = [Month, row above]

## Visit Report (Jan 2023)
VISIT REPORT
COMPANY |  | PT. Autocomp System Indonesia (PASI)
PROJECT NAME |  | PASI Maintenance Project
PERIOD |  | July 2021 - June 2022
REVISED DATE |  | 2022-03-01 | [6 empty] | Total Man-days
REVISED BY |  | TOS - Bayu, Yudha | [6 empty] | 0
NO. | DATE | PURPOSE / ACTIVITY | SUBJECT / PROJECT | AFFILIATE | REQUESTOR | ASSIGNEE | MAN-DAYS | REMARK | STATUS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## 1
Please put attachment here:
1. Issue screenshot
2. Evidence
3. Etc.